## Actions
Identifier | Action | Primary responsible party | Collaborator | Other responsible parties | start date | end date | Identified CO2e savings [tCO₂e/year]
A1 | Standardise ESD in planning | City Development |  |  | 2022-01-01 | 2030-06-30
A2 | Educate developers on existing ESD standards | Planning & Place |  |  | 2022-07-01 | 2030-06-30
A3 | Elevate ESD standards in planning | Planning & Place |  |  | 2022-07-01 | 2030-06-30
A4 | Design and deliver information regarding available financing options for ESD | Planning & Place |  |  | 2022-07-01 | 2030-06-30
A5 | Design and deliver incentives that encourage high ESD standards | Planning & Place |  |  | 2022-07-01 | 2030-06-30
A6 | Require new developments to provide electric vehicle ready infrastructure | Planning & Place |  |  | 2022-07-01 | 2030-06-30
A7 | Enforce ESD standards | Planning & Place |  |  | 2025-07-01 | 2027-06-30
A8 | Facilitate a solar-on-rentals scheme | Planning & Place |  |  | 2022-07-01 | 2030-06-30
A9 | Facilitate a energy efficiency retrofit scheme | Planning & Place |  |  | 2023-06-01 | 2025-07-01
A10 | Facilitate low emissions infrastructure | Infrastructure & Open Space |  |  | 2021-01-01 | 2030-12-31 | 100
A11 | Facilitate community renewable energy projects | Planning & Place |  |  | 2023-06-01 | 2028-07-01
A12 | Engage a specialist facilitator for industry groups focused on energy efficiency and decarbonisation | Planning & Place |  |  | 2022-07-01 | 2030-06-30
A13 | Seek expertise, advice and support from collaborators in research, business and sustainability | Planning & Place |  |  | 2022-07-01 | 2030-06-30
A14 | Engage key industry stakeholders to contribute expertise | Planning & Place |  |  | 2022-07-01 | 2030-06-30
A16 | Facilitate onsite power generation and sharing via rooftop solar and batteries | Planning & Place |  |  | 2022-01-01 | 2030-06-30
A17 | Explore group Power Purchase Agreement (PPA) opportunities | Planning & Place |  |  | 2023-07-01 | 2030-06-30
A18 | Support business to access finance mechanisms e.g., EUF loans for business and Energy Performance Contracts | Planning & Place | Sustainable Australia Fund |  | 2022-01-01 | 2030-06-30
A19 | Facilitate waste minimisation in business operations | Planning & Place |  |  | 2021-07-01 | 2030-06-30
A20 | Participate in a co-ordinated, regional approach with other SECCCA councils | Planning & Place |  |  | 2022-07-01 | 2030-06-30
A21 | Advocate to SEMMA and GSEM groups | Planning & Place |  |  | 2021-07-01 | 2030-06-30
A22 | Work with other levels of Government on program deployment across the region | Planning & Place |  |  | 2021-07-01 | 2030-06-30
A23 | Develop case studies and showcase positive examples from across the region | Planning & Place |  |  | 2023-01-01 | 2030-06-30
A24 | Embed sustainable economic development and a strong circular economy into Council policy and processes | Planning & Place |  |  | 2021-01-01 | 2030-06-30
A25 | Contribute to the planning of a rapid charging network and map across the SECCCA region | Planning & Place |  |  | 2022-01-01 | 2022-07-01
A26 | Implement Kingston's EV charging roadmap | Planning & Place |  |  | 2022-07-31 | 2030-12-31
A27 | Facilitate EV parking availability | Planning & Place |  |  | 2023-06-30 | 2030-06-30
A28 | Work with SECCCA on a regional approach for EVs | Planning & Place |  |  | 2023-06-30 | 2030-06-30
A29 | Work with other Victorian Climate Alliances to increase EV uptake | Planning & Place |  |  | 2023-06-30 | 2030-06-30
A30 | Assist business to trial new technologies including EVs | Planning & Place |  |  | 2023-06-30 | 2030-06-30
A31 | Allocate more road space to sustainable modes of transport | Infrastructure & Open Space |  | Planning & Place
A32 | Advocate for better public transport | Planning & Place
A33 | Support car share programs | Planning & Place |  |  | 2022-07-01 | 2027-07-01
A34 | Educate the community about sustainable transport | Planning & Place |  |  | 2022-01-01
A35 | Educate to combat misinformation on EVs | Planning & Place
A36 | Promote EV benefits and location of charging infrastructure | Planning & Place |  |  | 2022-07-01 | 2030-12-31
A37 | Provide incentives for the uptake of EVs | Planning & Place
A38 | Commit to Climate Emergency action in the Council Plan | Customer & Corporate Support |  |  | 2022-01-01 | 2029-06-30
A39 | Include Climate Emergency Key Performance Indicators for the Leadership Team | Customer & Corporate Support |  |  | 2022-07-01 | 2030-06-30
A40 | Regularly update Council's Audit & Risk Committee with relevant climate change information | Customer & Corporate Support |  |  | 2022-01-01 | 2030-06-30
A41 | Complete a gaps and opportunities assessment of Council policies, strategies and action plans | Customer & Corporate Support |  |  | 2022-07-01 | 2030-06-30
A42 | Establish a community advisory group focused on climate action | Customer & Corporate Support |  |  | 2022-07-01 | 2030-06-30
A43 | Complete quarterly reporting on Council’s response to the Climate and Ecological Emergency | Customer & Corporate Support |  |  | 2022-01-01 | 2030-06-30
A44 | Review and evaluate Kingston's community emissions reduction action plan using the modelling conducted to develop the plan | Planning & Place |  |  | 2022-07-01 | 2028-06-30
A45 | Develop a divestment strategy | Chief Finance Office |  |  | 2022-01-01 | 2030-06-30
A46 | Research investment opportunities for climate emergency action | Chief Finance Office; Planning & Place |  |  | 2022-01-01 | 2030-06-30
A47 | Embed environmentally sustainable economic development | Planning & Place |  | Kingston City Council | 2023-01-01 | 2030-06-30
A48 | Facilitate emission reduction activities in the industrial and business sector | Planning & Place |  |  | 2021-06-30 | 2030-06-30
A49 | Advocate for business to adopt ‘climate risk disclosure and net zero planning’ as standard practice | Planning & Place |  |  | 2025-06-30 | 2030-06-30
A50 | Include requirements to address environmental impacts in leases of Council property | Chief Finance Office |  |  | 2022-07-01 | 2030-06-30
A51 | Phase out single use plastics across Council operations | Infrastructure & Open Space |  |  | 2021-07-01 | 2030-06-30
A52 | Engage the community to reduce plastics | Infrastructure & Open Space |  |  | 2022-07-01 | 2030-06-30
A53 | Support organic recycling across business and industry | Infrastructure & Open Space
A54 | Implement legislative requirements aimed at significantly reducing waste to landfill | Infrastructure & Open Space
A55 | Negotiate contracts that maximise resource efficiency and reduce waste | Infrastructure & Open Space |  |  | 2022-07-01 | 2030-07-01
A56 | Develop and implement training for staff focussed on Council’s response to the Climate and Ecological Emergency | Customer & Corporate Support |  |  | 2022-07-01 | 2030-06-30
A57 | Embed competencies relevant to climate emergency action into staff roles | Customer & Corporate Support |  |  | 2023-06-30 | 2030-06-30
A58 | Collaborate with Traditional Owners on Council’s Climate and Ecological Emergency response | Customer & Corporate Support |  |  | 2022-07-01 | 2030-06-30
A59 | Recognise the Climate and Ecological Emergency in Council’s Reconciliation Action Plan | Customer & Corporate Support |  |  | 2021-06-30 | 2030-06-30
A60 | Continue energy efficiency upgrades across Council buildings | Infrastructure & Open Space |  |  | 2022-07-01 | 2025-12-31
A61 | Procure renewable energy including for small market sites | Chief Finance Office |  |  | 2022-07-01 | 2025-12-31
A62 | Transition Council buildings away from gas | Infrastructure & Open Space |  |  | 2022-07-01 | 2025-12-31 | 1273
A63 | Transition Council’s fleet | Chief Finance Office |  |  | 2022-07-01 | 2026-06-30 | 721
A64 | Mitigate and build community resilience to the heat impacts of climate change | Planning & Place |  |  | 2021-07-01 | 2028-07-01
A65 | Support and educate the community about the importance of biodiversity | Planning & Place |  |  | 2023-07-01 | 2026-07-01
A66 | Deliver evidence based environmental education for the community to stay informed, connected and take action | Planning & Place |  |  | 2023-07-01 | 2026-06-30
A67 | Participate in ASPIRE | Planning & Place |  |  | 2022-07-01
A68 | Offer low carbon community grants for organisations and initiatives that prioritise low emissions | Community Strengthening |  |  | 2022-07-01 | 2025-07-01
A69 | Deliver 'zero waste' Council events | Community Strengthening | Kingston City Council |  | 2022-07-01 | 2025-07-01
A70 | Develop and implement Council’s advocacy priorities to address the Climate and Ecological Emergency | Customer & Corporate Support | Planning & Place |  | 2022-07-01 | 2025-07-01
A71 | Implement a communications and engagement strategy aimed at empowering the community | Planning & Place | Customer & Corporate Support |  | 2023-07-01 | 2025-07-01
A72 | Consider use of the UN's Sustainable Development Goals (SDGs) | Customer & Corporate Support | Planning & Place | Kingston City Council | 2022-07-01 | 2030-06-30
A73 | Implement Council’s Urban Forest Strategy | Planning & Place | Infrastructure & Open Space |  | 2022-07-01 | 2030-07-01
A75 | Investigate opportunities to collaborate on carbon ‘sinks’ | Planning & Place |  |  | 2025-07-01 | 2028-07-01
A74 | Offset residual Council emissions | Chief Finance Office | Planning & Place |  | 2025-07-01 | 2028-07-01 | 5000
A76 | Develop and deliver a Climate Adaptation Plan | Planning & Place |  |  | 2024-07-01 | 2027-07-01
A77 | Develop and deliver Council's Public Health and Wellbeing Plan including climate change considerations | Community Strengthening |  |  | 2022-07-01 | 2029-06-30