## Actions
Identifier | Action | Implementation phase | Status | Tasks | Indicators | Has goals | Primary responsible party | Collaborator | Other responsible parties | updated at
AQ-1 | Increase inspections of emissions from oil and gas sites | Continuous Action | On time |  | 1 | Yes | Strategic Integration |  |  | 2025-01-15 15:18
AQ-2 | Expand air quality information and monitoring | Implementation | On time | • Share Longmont's Air Quality findings with legislators [completed Oct. 11, 2023] • Share Longmont's Air Quality findings with legislators [completed June 10, 2024] | 2 | Yes | Strategic Integration |  |  | 2025-01-17 14:23
AQ-3 | Develop an Ozone Reduction Incentive and Enforcement Program | Not started | Late |  | 1 | Yes | Strategic Integration |  |  | 2025-01-16 11:16
AQ-4 | Adopt and enforce leak detection and repair associated with oil and gas operations | Implementation | On time | • Oppose the drilling of Blue Paintbrush oil and gas wells [completed May 31, 2023] • Closure of Oil and Gas Wells within the City of Longmont [completed June 28, 2021] | 2 | Yes | Strategic Integration |  |  | 2025-01-16 11:17
BI-1 | Expand indoor air quality testing program | Implementation | On time |  | 2 | Yes | Environmental Affairs |  |  | 2025-01-16 11:17
BI-2 | Preserve, improve, and rehabilitate existing affordable homes | Implementation | On time | • Longmont Housing Authority: The Suites Doors Replacement [not started, due date: Dec. 31, 2025] | 3 | Yes | Housing and Community Investment |  |  | 2025-01-06 15:52
BI-3 | Develop and implement a process to incorporate social equity into prioritizing infrastructure improvements | Implementation | Late | • Community Asset Mapping [in progress, due date: Dec. 31, 2025] • Equity into the CIP Budget [completed May 31, 2022] | 0 | No | Sustainability |  |  | 2025-07-15 15:56
BI-4 | Require life cycle cost and sustainability analyses for all City of Longmont projects and programs | Implementation | Late | • Incorporating sustainability into the Project Management Office [in progress, due date: Aug. 31, 2025] • Internal Sustainable Design Guide Update [completed Dec. 29, 2023] • Internal Sustainability Evaluation System (SES) Update [completed May 19, 2023] | 1 | No | Sustainability |  |  | 2025-07-15 15:42
BI-5 | Revise and update the City of Longmont design standards and construction specifications to include sustainability | Implementation | Late |  | 6 | Yes | Public Works and Engineering |  |  | 2024-12-30 11:28
BI-6 | Develop 'Beyond' building code | Implementation | Late | • New Code Cost Analysis [in progress, due date: May 31, 2025] • Present to City Council to seek guidance on 2024 code adoptions for energy code. [in progress, due date: Feb. 11, 2025] | 3 | Yes | Building Inspection |  |  | 2025-01-13 05:00
BI-7 | Adopt and enforce updated building code | Implementation | On time | • Adoption of the 2024 ICC Building Codes [in progress, due date: Jan. 1, 2026] | 5 | Yes | Building Inspection |  |  | 2025-01-17 09:39
C-1 | Expand existing neighborhood programs to enhance sustainability, resiliency, and quality of life | Implementation | On time | • Award sustainability grants to active neighborhood groups through the Sustainable Neighborhood Solutions and Neighborhood Improvement Program [in progress, due date: Dec. 31, 2024] • Include a special water conservation educational series in the Neighborhood Leadership Series training program in 2024 [completed Aug. 17, 2024] | 2 | Yes | Community & Neighborhood Resources | Sustainability |  | 2025-07-10 11:36
C-2 | Develop an inclusive standard of equitable access and opportunity for all residents that enhances capacity and is implemented uniformly across all city departments, policies, programs, and outcomes | Implementation | On time | • 2022 and 2023 Equity Team Projects [completed Dec. 31, 2023] • Launch Internal Equity Team [completed Nov. 30, 2021] | 1 | Yes | Community & Neighborhood Resources |  |  | 2025-07-15 15:50
C-3 | Collaborate with St. Vrain Valley School District on a preparedness and resilience site | Not started | On hold |  | 0 | No | Longmont Power & Communications |  |  | 2024-12-26 08:50
C-4 | Incorporate the City of Longmont's Community Engagement Model into all city plans and projects | Implementation | On time | • Update the staff guide for working with translators and interpreters [in progress, due date: Dec. 31, 2025] • Provide Community Engagement Training [completed April 4, 2024] • Incorporate Community Engagement into Project Management Office tracking [completed Dec. 27, 2024] • Update the Community Involvement Manual [completed Dec. 29, 2023] | 0 | No | City Manager's Office |  |  | 2025-07-09 10:56
EV-1 | Create a Longmont Sustainable Business Recognition Program (SBP) | Implementation | On time | • Launch the Induction Cooktop Program. [completed Jan. 1, 2025] • Induction Cooktop Pilot Program [completed Jan. 1, 2024] • To-Go Ware Program [completed May 31, 2023] | 1 | No | Sustainability |  |  | 2025-06-02 10:03
EV-2 | Work with local economic development organizations to support local businesses and attract and expand Green Industry/Clean Tech jobs | Not started | On hold |  | 1 | No | External Services |  |  | 2024-07-15 13:40
EV-3 | Reinstate the Pollution Prevention Program | Not started | On hold |  | 0 | No | Sustainability |  |  | 2023-04-21 14:41
EV-4 | Establish and promote a City of Longmont internal Sustainable Purchasing Policy | Implementation | On time | • Sustainable Purchasing Policy [completed Dec. 31, 2024] • Staff Training on Sustainable Purchasing [completed April 23, 2024] | 4 | Yes | Purchasing and Contracts |  |  | 2025-01-16 09:43
EV-5 | Identify needs, barriers and opportunities to establish equitable access for underutilized, under-represented, and/or multi-cultural businesses and support through expanded programming | Implementation |  |  | 0 | No | External Services |  |  | 2024-01-31 15:12
EV-6 | Partner with local educational institutions to connect sustainability knowledge and workforce needs | Implementation |  |  | 2 | Yes | External Services |  |  | 2025-02-13 11:40
E-1 | Review energy efficiency improvement and renewable energy generation opportunities for municipal facilities | Implementation | On time | • Solar Photovoltaic (PV) Installations [in progress, due date: Dec. 31, 2024] • Energy Efficiency Lighting Installs [completed Dec. 31, 2023] • Renewable and Clean Energy Challenge Grant [completed Dec. 31, 2024] | 3 | Yes | Longmont Power & Communications; Sustainability |  |  | 2025-01-19 08:52
E-2 | Continue collaboration with Energy Outreach Colorado to expand energy services for low-income households | Implementation | Late |  | 1 | Yes | Longmont Power & Communications |  |  | 2025-07-11 10:45
E-3 | Improve commercial building efficiency | Implementation | On time |  | 2 | Yes | Longmont Power & Communications |  |  | 2025-01-03 16:19
E-4 | Develop a comprehensive 100% renewable electricity plan for Longmont's Just Transition to a Clean Energy Economy | Implementation | On time | • New Membership Growth & Involvement [completed Dec. 31, 2024] • Equity Learning & Membership Growth [completed Dec. 30, 2023] • Implementation of Climate Action Equity Discussion Guide [completed Dec. 30, 2022] • Implementation of Climate Action Equity Discussion Guide [completed Jan. 1, 2021] • Enviromental Equity Learning with the City [completed Dec. 8, 2020] • Engaging Frontline Communities [completed Aug. 1, 2019] | 1 | No | Sustainability |  |  | 2025-01-06 12:29
E-5 | Report and benchmark energy use | Implementation | Late | • Resources for benchmarking customers [completed Dec. 31, 2024] • Automated Portal [completed Nov. 30, 2022] | 1 | No | Longmont Power & Communications |  |  | 2025-01-16 12:34
E-6 | Monitor Advanced Metering Infrastructure implementation | Implementation | On time | • AMI Meter Installation [in progress, due date: Dec. 1, 2024] | 2 | Yes | Longmont Power & Communications |  |  | 2025-01-19 08:45
E-7 | Continue to provide energy efficiency outreach and incentives for all energy users | Implementation | On time |  | 1 | Yes | Longmont Power & Communications |  |  | 2025-02-10 19:01
E-8 | Monitor and reduce greenhouse gas emissions | Implementation | On time | • 2024 Greenhouse Gas inventory [in progress, due date: Dec. 31, 2025] • 2021 Greenhouse Gas Inventory [completed July 1, 2023] • 2019 Greenhouse Gas Inventory [completed June 17, 2020] • 2016 Greenhouse Gas Inventory [completed March 1, 2019] | 1 | Yes | Sustainability |  |  | 2025-07-09 09:37
E-9 | Expand awareness and partnership opportunities for solar installations and renewable subscriptions | Implementation | On time | • City Roof-Mounted Community Solar [in progress, due date: Dec. 31, 2024] | 2 | No | Longmont Power & Communications |  |  | 2025-01-17 14:25
FS-1 | Identify barriers and opportunities for local food production | Not started | Late |  | 1 | Yes | Sustainability |  |  | 2024-12-26 08:51
FS-2 | Encourage and support the Boulder County Resource Conservation Board in pursuing carbon sequestration studies | Planning | On hold |  | 0 | No | Sustainability |  |  | 2024-12-26 08:55
FS-3 | Expand connections between local food producers and areas/populations in need | Not started | On hold |  | 1 | No | Sustainability |  |  | 2024-12-26 08:56
FS-4 | Support and expand Garden to Cafeteria Program opportunities | Not started | On time |  | 0 | No | Sustainability |  |  | 2024-12-26 08:57
FS-5 | Support the establishment of community food processing and storage facilities in partnership with Boulder County | Not started | On time |  | 0 | No | Sustainability |  |  | 2024-12-26 08:58
FS-6 | Encourage and support agricultural research in Boulder County | Implementation | On time | • Hire 5-year term Project Manager II (Open Space & Agriculture) [completed May 1, 2025] | 0 | No | Parks and Natural Resources |  |  | 2025-07-10 11:07
NE-1 | Update the Open Space Master Plan | Completed |  | • Update the Open Space Master Plan [completed July 17, 2018] | 0 | No | Open Space |  |  | 2024-08-26 12:44
NE-2 | Update the Wildlife Management Plan | Completed |  | • Update the Wildlife Management Plan [completed Sept. 24, 2019] | 0 | No | Open Space |  |  | 2024-08-26 12:45
NE-3 | Work with community partners to promote education and awareness about water-wise landscaping and integrated pest management practices on private properties | Implementation | On time | • Education and Outreach [completed Dec. 31, 2024] • Rebates Sold [completed Dec. 31, 2024] • Longmont Water Fair [completed June 9, 2024] | 1 | No | Water Resources |  |  | 2025-07-01 10:22
NE-4 | Update the Tree Canopy Management and Replacement Plan | Implementation | On time | • Update the Tree Canopy [completed Dec. 31, 2022] | 3 | No | Forestry |  |  | 2025-01-17 09:05
NE-5 | Create and implement a plan to restore and remediate damaged ecologically sensitive areas and critical corridors and habitat areas | Implementation | On time | • Begin data collection for stewardship plans for City properties [in progress, due date: Jan. 1, 2026] • Initiate native plant propagation utilizing the greenhouse [completed March 31, 2025] • Request and hire Senior Plant Ecologist position [completed July 15, 2024] | 1 | No | Open Space |  |  | 2025-07-10 11:04
NE-6 | Continue and increase participation in existing volunteer programs | Implementation | On time | • Nature Everywhere Grant: Increase equitable access to the outdoors and outdoor programming for youth and families [in progress, due date: Oct. 1, 2025] • Convert part-time Volunteer Projects Coordinator and Sandstone Ranch Volunteer Coordinator positions to full time. Updated job titles: Volunteer Coordinator and Environmental Education Coordinator. [in progress, due date: Feb. 28, 2025] • GOCO Grant with Wildlands Restoration Volunteers [completed Dec. 31, 2022] • Launch new volunteer opportunities: Trail Ambassadors and Citizen Scientists-Phenology [completed Dec. 31, 2022] • Hire a Volunteer Coordinator [completed June 30, 2021] | 1 | No | Open Space |  |  | 2025-01-17 13:00
T-1 | Coordinate with RTD to expand service and hours to key community locations | Implementation | On time |  | 1 | No | Transportation Planning & Airport |  |  | 2024-12-31 10:35
T-2 | Develop a Fleet Efficiency and Alternative Fuels Plan | Implementation | On time | • 2023 Charge Ahead Colorado Grant: EV Charging Stations [in progress, due date: April 30, 2025] | 1 | Yes | Fleet Services |  |  | 2025-07-10 06:36
T-3 | Coordinate with regional partners on publicizing car/van pooling | Implementation | On time | • 2024 Tasks [completed Dec. 31, 2024] • 2023 Tasks [completed Dec. 31, 2023] • 2022 Tasks [completed Dec. 31, 2022] | 2 | No | Planning Development Services |  |  | 2025-01-10 13:54
T-4 | Increase electric vehicles through vehicle incentives and improved infrastructure | Implementation | On time | • Launch electric vehicle charger rebate [completed Sept. 30, 2022] • Xcel Energy Partners in Energy Program: A Regional Transportation Electrification Plan for Boulder County Communities [completed Aug. 12, 2022] | 1 | Yes | Sustainability; Longmont Power & Communications |  |  | 2025-01-07 19:00
T-5 | Audit all transit stops to evaluate accommodation needs of all residents and prioritize improvements | Implementation | On time | • Next Steps for Transit Stop Improvements [completed Dec. 31, 2024] • Local Longmont bus stop survey [completed Dec. 31, 2023] • 2022 Bus Stop Improvements [completed Dec. 31, 2022] | 1 | No | Sustainability; Planning Development Services |  |  | 2025-01-24 10:08
T-6 | Support growth in active transportation and transit ridership through implementation of the Multimodal Transportation Plan | Implementation | On time | • New Bus Rapid Transit Service [in progress, due date: Sept. 30, 2026] • Mobility and Transit Hub at 1st and Main [in progress, due date: Sept. 30, 2026] • Coffman Street Multimodal Corridor [in progress, due date: Dec. 31, 2025] • Update the Longmont Multimodal Transportation Implementation Plan [in progress, due date: Dec. 31, 2024] | 3 | No | Transportation Planning & Airport |  |  | 2024-12-30 11:23
T-7 | Continue the Ride Free Transit Program | Implementation | On time |  | 1 | No | Transportation Planning & Airport |  |  | 2024-12-31 10:32
WA-1 | Build support for participation in the Curbside Composting Program | Implementation | On time |  | 1 | No | Waste Services Operations; Sustainability |  |  | 2023-10-25 08:19
WA-2 | Provide Waste Diversion Opportunities and Education for St. Vrain Valley School District | Implementation | On time |  | 1 | Yes | Sustainability | Waste Services Operations |  | 2025-01-09 11:15
WA-3 | Develop a strategic waste management plan with regional partners | Implementation | On time |  | 1 | Yes | Waste Services Operations; Sustainability |  |  | 2025-06-02 09:23
WA-4 | Increase public education and awareness about waste reduction and diversion opportunities | Implementation | On time | • Longmont Waste Services Mobile App [completed Aug. 6, 2019] | 3 | Yes | Waste Services Operations; Sustainability |  |  | 2025-06-02 09:24
WA-5 | Incorporate diversion target for city construction projects and Longmont Urban Renewal Authority (LURA) projects into standard contract language | Implementation | On time | • Environmentally Preferable Purchasing Policy (EP3) [in progress, due date: March 15, 2025] | 1 | No | Purchasing and Contracts |  |  | 2025-01-16 09:52
WA-6 | Adopt a Commercial Recycling Ordinance that Includes Multifamily Properties | Implementation | On time | • URO Phase V Implementation [in progress, due date: Jan. 1, 2029] • URO Phase IV Implementation [in progress, due date: June 1, 2025] • URO Phase III Implementation [completed Jan. 1, 2025] • URO Phase II Implementation [completed June 1, 2024] • URO Phase I Implementation [completed Jan. 1, 2024] • URO Passed in City Council [completed July 11, 2023] • URO Draft [completed June 1, 2023] | 2 | No | Sustainability; Waste Services Operations |  |  | 2025-01-09 12:01
WA-7 | Increase hazardous/e-waste/materials drop-off opportunities | Implementation | On time | • 2024 Annual Collection Events [completed Dec. 31, 2024] • 2023 Annual Collection Events [completed Dec. 31, 2023] • 2022 Annual Collection Events [completed Dec. 31, 2022] | 2 | Yes | Waste Services Operations; Sustainability |  |  | 2025-06-02 09:24
WA-8 | Establish a Construction Demolition Waste Incentive Program | Planning | On time |  | 1 | No | Planning Development Services |  |  | 2025-06-02 09:55
W-1 | Implement identified strategies within the Water Efficiency Plan | Implementation | On time | • Water Efficiency Master Plan Update [completed Jan. 14, 2025] • Non-Function Turf Replacement Plan [completed Oct. 1, 2024] • Water Efficient Code Evaluation Report [completed July 10, 2024] • Longmont Water Fair [completed June 9, 2024] • Kensington Park Turf Transition project [completed Sept. 23, 2023] • Water Communications Plan [completed Dec. 31, 2022] • Sonoran Institute Growing Water Smart Workshop [completed Sept. 30, 2022] | 2 | No | Water Resources |  |  | 2025-07-01 10:25
W-2 | Complete an analysis of water loss and recommend strategies for subsequent actions | Implementation | On time | • Continuous Use Notifications [in progress, due date: Dec. 31, 2024] • Automated Meter Reading (AMR) [in progress, due date: Dec. 31, 2023] | 2 | No | Water Resources |  |  | 2025-07-01 10:26
W-3 | Develop a Strategic Water Quality Improvement and Enforcement Plan for consecutive systems | Not started | On hold |  | 1 | No | Environmental Affairs |  |  | 2025-07-03 13:34
W-4 | Coordinate with Boulder County Public Health on Model Greywater (water reuse) ordinance | Not started | On hold |  | 0 | No | Water Resources |  |  | 2025-07-01 10:27
W-5 | Create an active Watershed Management Program | Planning | On time | • 2023 Keep It Clean Outreach [completed Dec. 31, 2023] • Button Rock Management Plan [completed April 25, 2023] | 0 | No | Environmental Affairs |  |  | 2025-01-17 15:03