## Actions
Identifier | Action | Implementation phase | Status | Tasks | Primary responsible party | Collaborator | Other responsible parties | Indicators | Has goals | updated at
BI1 | Develop and implement an Amenity Tree Management Policy | Completed | On time | • Develop a new Stevenage Tree & Woodland Strategy [completed 4 Jun 2025] • Develop an Amenity Tree Management Policy [completed 20 Jan 2021] | Direct Services |  |  | 0 | No | 2025-06-24 14:07
BI2 | Implement and update tree replacement policies and strategies | Underway | On time | • New tree replacement policies in the Local Plan [in progress, due date: 31 Dec 2025] • Include tree replacement policy in the Amenity Tree Management Policy [completed 20 Jan 2021] | Planning & Regulation |  |  | 0 | No | 2025-06-03 14:06
BI3 | Plant 4,000 trees in Stevenage by 2030 | Completed | On time | • Create 3 new micro woods [completed 31 Jan 2025] • Orchard Creation [completed 31 Dec 2023] • Create a new community woodland in Fairlands Valley Park [completed 24 Feb 2023] | Direct Services |  |  | 1 | No | 2025-06-03 14:06
BI4 | Update, deliver, and monitor the Stevenage Biodiversity Action Plan (BAP) | Completed | On time | • Present to E&E Select Committee: final revision of 2024-2028 BAP. [completed 27 Feb 2024] • 2024-2028 revision presented to Cabinet for final approval and ratification. [completed 9 Oct 2024] • Final reiteration of the 2024-2028 revision produced. [completed 9 Oct 2024] • Commission Herts & Middlesex Wildlife Trust to review the current BAP [completed 30 Apr 2023] | Direct Services |  |  | 0 | No | 2025-06-03 14:06
BI5 | Develop a Meadow Management Framework | Underway | On time | • Agree additional grassland meadow sites [in progress, due date: 30 Sep 2025] • Deliver additional grassland management sites [completed 25 Mar 2022] | Direct Services |  |  | 0 | No | 2025-06-24 14:08
BI6 | Identify and measure Carbon Sinks | Planning stage | On time | • Identify potential large carbon storage habitats within Stevenage [in progress, due date: 31 Dec 2025] | Direct Services | Planning & Regulation |  | 0 | No | 2025-06-24 14:09
BI8 | Implement and monitor Biodiversity Net Gain (BNG) | Underway | On time |  |  |  |  | 0 | No | 2025-06-24 14:10
BI7 | Creation of Community Orchards | Continuous Action | On time | • Orchard management training provided to Green Space Volunteers to support ongoing management of the community orchards [in progress, due date: 31 Dec 2025] • New community orchard planted at Peartree Park, Letchmore Road Open Space and Bedwell Park [completed 15 Nov 2022] • New community orchards planted at Shephalbury Park, St Nicholas Park and Raleigh Crescent Open Space [completed 2 Dec 2021] • New community orchard in Hampson Park [completed 16 Mar 2021] • New community orchard in Wellfield Open Space [completed 16 Mar 2021] • New community orchard in Donkey Park [completed 16 Mar 2021] • New community orchard in Symonds Green [completed 31 Mar 2020] | Direct Services |  |  | 0 | No | 2025-06-24 14:10
BI9 | Develop and implement a Green Spaces Strategy | Completed | On time | • Green Spaces Strategy approved by Cabinet [completed 4 Jun 2025] • Present to E&E Select Committee [completed 20 Mar 2025] • Public consultation to seek feedback on the draft Green Spaces Strategy [completed 23 Feb 2025] • Public engagement to inform site specific management plans for each of the principal parks [completed 15 Sep 2024] • Public consultation to inform the development of the strategy [completed 7 Jan 2024] |  |  |  | 0 | No | 2025-06-18 14:38
BI10 | Develop and implement a Tree & Woodland Strategy | Completed | On time | • Strategy approved by Cabinet [completed 4 Jun 2025] • Present to E&E Select Committee [completed 20 Mar 2025] • Public consultation to seek feedback on the draft Tree & Woodland Strategy [completed 23 Feb 2025] • Public consultation to inform the development of the strategy [completed 5 Jan 2025] |  |  |  | 0 | No | 2025-06-18 14:41
BU1 | Support corporate sustainability for local businesses | Underway | On time | • Wenta's Action Zero Programme: Net-zero support for SMEs [in progress, due date: 31 Mar 2026] • Create a webpage on sustainable business practice [completed 6 Feb 2024] • Sustainability support through Community Renewal Funding programme [completed 31 Mar 2023] • Grow through Sustainability Conference 2022 [completed 15 Mar 2022] | Planning & Regulation |  |  | 0 | No | 2025-07-02 15:56
BU2 | Develop and implement a Sustainable Business Programme | Underway | On time | • Small Business Sustainability Support [in progress, due date: 31 Mar 2026] • Stevenage Green Business Grant [in progress, due date: 30 Sep 2025] • Second Meet the Buyer Event (MTB) [completed 25 Jun 2024] • Phase 2: 1 Day intensive workshop for medium sized businesses [completed 20 Nov 2023] • First Meet the Buyer Event (MTB) [completed 23 Sep 2023] | Planning & Regulation |  |  | 0 | No | 2025-07-02 15:57
BU3 | Implement sustainable procurement for the Council | Underway | On time | • Include and monitor Social Value considerations in Council's procurement processes [in progress, due date: 31 Mar 2026] • Update and revise the Cooperative Procurement Strategy for 2025-2028 [completed 12 Mar 2025] • Participate in the RCCF Sustainable Procurement Sub Group [completed 31 Mar 2025] • Take part in the EELGA Responsible Procurement Diagnostic project [completed 31 Mar 2024] • Develop a Cooperative Procurement Strategy [completed 23 Nov 2021] | Finance and Estates | Planning & Regulation |  | 0 | No | 2025-07-02 16:00
CR1 | Integrate sustainability & climate resilience within the SG1 Regeneration Programme | Completed | On time | • Include climate change principles in the SG1 development proposal. [completed 30 May 2023] • Submitted Planning Supporting Documents, including Energy Strategy, Sustainability Statement, Ecological enhancement Strategy, Transport Assessment, Air Quality Assessment, Noise Impact Assessment. Flood Risk Assessment. [completed 24 Dec 2019] | Planning & Regulation |  |  | 0 | No | 2025-06-26 13:33
CR2 | Update the Local Plan to incorporate new climate policies | Underway | On time | • Upgrade the Local Plan with improved Climate Change considerations [in progress, due date: 31 Dec 2025] • Implement Stevenage Design Guide with Climate Change considerations [completed 1 Jan 2023] • To include climate change considerations in the local plan [completed 31 Dec 2020] | Planning & Regulation |  |  | 0 | No | 2025-06-26 13:37
CR3 | Zero carbon development for Station Gateway Area Action Plan (AAP) | Underway | On time | • Submission of the Local Plan to the Secretary of State [not started, due date: 30 Jun 2025] • Consult AAP/Local Plan Review through a Regulation 19 consultation [completed 14 Feb 2025] • Consult changes of AAP/Local Plan Review through a Regulation 18 consultation [completed 15 Aug 2025] • Incorporate AAP into Local Plan Review [completed 5 Jul 2025] • Public and Stakeholder consultation on the draft Preferred Options Report [completed 18 Jul 2023] • Responses to the public consultation on the Stevenage Connection Area Action Plan: Issues and Options Report. [completed 6 Sep 2021] • Public consultation on the Stevenage Connection Area Action Plan: Issues and Options Report. [completed 5 Sep 2021] • Publish the Sustainability Appraisal and Strategic Environmental Assessment screening [completed 22 May 2019] | Planning & Regulation |  |  | 0 | No | 2025-07-04 15:58
CR4 | Incorporate sustainability aspects into the new Railway North Multi Storey Car Park (MSCP) | Completed | On time | • Construction complete [completed 5 May 2023] • Construction begins [completed 23 May 2022] | Regeneration | Planning & Regulation |  | 0 | No | 2025-06-03 14:13
EW1 | Free Water Refill in Town | Continuous Action |  |  | Planning & Regulation |  |  | 0 | No | 2025-06-13 15:28
EW2 | Rainwater Harvesting Pilot | Completed | On time | • Investigate additional opportunities for installing rainwater harvesting systems at Council's allotment sites [not started, due date: 1 Jul 2026] • Peartree Rainwater Collection Pilot [completed 31 Aug 2024] • Install 6 Water Butts at Garage Site on Whitesmead Road [completed 18 Oct 2023] | Direct Services | Planning & Regulation |  | 0 | No | 2025-06-25 15:21
EW3 | Reduce domestic water utilisation and improve efficiency | Underway | On time | • Tenant Welcome Packs: Water Saving Tips [not started, due date: 31 Dec 2025] • Enhance Water Efficiency related Policies within the Stevenage Local Plan [in progress, due date: 31 Dec 2025] | Planning & Regulation |  | Affinity Water | 0 | No | 2025-06-26 14:47
EW4 | Decarbonise energy supply at Council's sites and buildings | Underway | On time | • Energy upgrades at SBC leisure facilities [in progress, due date: 31 Dec 2025] • St George’s and Westgate Multi Storey Car Park (MSCP) upgrade programme [in progress, due date: 31 Dec 2025] • Electricity monitoring through Grid Edge platform to identify efficiency opportunities [in progress, due date: 31 Dec 2025] • Conduct energy audits across SBC sites (electricity and gas) [completed 31 Jul 2023] • Boiler upgrade for SBC shelter housing [completed 31 Dec 2022] | Facilities | Finance and Estates; Planning & Regulation |  | 0 | No | 2025-06-25 07:38
EW5 | Zero carbon tariff for SBC electricity corporate contract | Completed | On time | • Switching to zero carbon electricity supply for SBC corporate contract [completed 4 Apr 2022] | Planning & Regulation |  |  | 0 | No | 2025-06-03 14:16
EW6 | Increase local renewable energy generation | Initial scoping | On time | • Incorporate policies to support renewable energy generation in the Local Plan [in progress, due date: 31 Dec 2025] • Solar Together Hertfordshire Scheme [completed 13 Jun 2025] • Complete a feasibility study on PV and battery storage installation for St George's Car Park alongside energy usage reduction [completed 1 May 2024] • Install Solar Panels on the New Railway North MSCP Development [completed 5 May 2023] | Planning & Regulation | Regeneration; Finance and Estates |  | 2 | No | 2025-06-13 15:36
HO1 | Decarbonisation of SBC Social Housing | Underway | On time | • Delivery of the Warm Homes: Social Housing Fund (Wave 3) [in progress, due date: 1 Jun 2028] • Delivery of the Social Housing Decarbonisation Fund Wave 2.1 [completed 17 Jun 2025] • Bid for Warm Homes: Social Housing Fund Wave 3 [completed 25 Nov 2024] • Delivery of the Social Housing Decarbonisation Funding - Wave 1 [completed 31 Dec 2023] • Bid for Social Housing Decarbonisation Fund - Wave 2.1 [completed 31 Mar 2023] | Housing & Investment |  |  | 1 | Yes | 2025-07-30 15:52
HO2 | Monitoring of Social Housing Energy Efficiency | Underway | On time | • Monitor the Council's housing stock using an Intelligent Energy System [in progress, due date: 31 Mar 2026] • Implement an Intelligent Energy System [completed 31 Dec 2022] | Housing & Investment |  |  | 0 | No | 2025-06-20 12:13
HO3 | Development of new sustainable Social Housing | Underway | On time | • Helston House, Scarborough Avenue [completed 29 Dec 2023] | Housing & Investment |  |  | 0 | No | 2025-06-20 12:55
HO4 | Garages refurbishment and improvement programmes | Completed | On time | • SBC Garages Asset Management Plan [in progress, due date: 30 Apr 2025] • Garages Refurbishment Programme [completed 31 Aug 2024] | Garages | Direct Services |  | 0 | No | 2025-06-20 16:17
HO5 | Decarbonisation of existing private domestic housing | Underway | On time | • Deliver Warm Homes Local Grant (WHLG) [in progress, due date: 31 Mar 2028] • Energy Company Obligation Scheme Round 4 (ECO 4) [in progress, due date: 31 Mar 2026] • Solar Together 2025 [completed 25 Apr 2025] • Home Upgrade Grant Phase 2 (HUG2) [completed 2 Dec 2024] • Submit EOI to Warm Homes: Local Grant [completed 1 Dec 2024] • Hertfordshire Energy Advice Tool (HEAT) app [completed 31 Dec 2023] • Promotion of the Solar Together Scheme [completed 27 Oct 2023] • Sustainable Warmth Funding [completed 31 Mar 2023] • Local Authority Delivery Scheme 2 (LAD2) [completed 30 Sep 2022] • Local Authority Delivery Scheme 1B (LAD1B) [completed 31 May 2022] • Energy Company Obligation Scheme round 3 (ECO 3) [completed 31 Mar 2022] | Planning & Regulation |  |  | 1 | No | 2025-06-24 09:43
HO6 | Communal heating upgrade of Sheltered Housing | Completed | On time |  | Housing & Investment |  |  | 1 | No | 2025-06-20 15:57
PA1 | Implement Climate Emergency education for residents & visitors | Underway | On time | • Incorporate a sustainability leaflet and flyer in to housing welcome packs. [not started, due date: 31 Dec 2025] • Stevenage Day 2025 [completed 8 Jun 2025] • Climate/Environmental Dates Calendar 2025 [completed 31 Dec 2024] • Stevenage Day 2024 [completed 6 Jul 2024] • Develop a Climate Change Communications Programme [completed 28 Jun 2024] • Stevenage Day 2023 [completed 10 Jun 2023] • Special storytime at Stevenage Central library [completed 15 Apr 2023] | Corporate Strategy & Transformation | Planning & Regulation |  | 0 | No | 2025-06-13 15:12
PA2 | Participate in the Council's Climate Action Scorecards assessment | Underway | On time | • Review Scorecards 2025 results [not started, due date: 30 Sep 2025] • Submit responses to Climate Action Scorecards 2025 [completed 31 Dec 2024] | Planning & Regulation |  |  | 0 | No | 2025-06-13 15:17
PA3 | Develop a Council's Climate Change Risk Assessment and Action Plan | Underway | On time | • Incorporate identified climate risks into the Operational Risks [in progress, due date: 31 Dec 2025] • Update the CCRA aligned with a DEFRA Adaptation Reporting Power (ARP) pilot project [completed 20 Jun 2025] • SBC First Climate Change Risk Assessment [completed 6 Aug 2024] • Service leads to review identified climate risks draft [completed 14 Jun 2024] • Climate Action team to draft climate risks [completed 10 Apr 2024] • Complete an Extreme Weather Survey [completed 30 Jun 2023] | Planning & Regulation |  |  | 0 | No | 2025-06-24 11:34
PA4 | Develop and implement a Climate Change Community Fund (CCCF) | Underway | On time | • Continuously assess, approve, fund and monitor CCCF projects [in progress, due date: 31 Mar 2026] • Develop the vision and define the scopes for the Street Plan [in progress, due date: 31 Oct 2025] • Revise the CCCF Requirements and Application Process [completed 7 Jun 2024] • Create and Publish the CCCF Webpage [completed 7 Jun 2024] • Design and Distribute a CCCF Flyer [completed 31 Jan 2024] • Test 2 Pilot Projects [completed 31 Mar 2024] | Planning & Regulation |  |  | 0 | No | 2025-06-13 15:18
PA5 | Promote event sustainability across the town | Underway | On time | • Discourage single-use plastic at refreshment and catering units at SBC events. [completed 6 Jul 2024] • Develop Sustainability Guidance as an integral part of the Community Event Toolkit [completed 24 May 2024] | Communities & Neighbourhoods |  |  | 0 | No | 2025-06-06 15:38
PA6 | Add "Tackling Climate Change" as priority of our Council's Corporate Plan | Completed | [5 empty] | 0 | No | 2025-06-03 14:31
PA9 | Establish an internal Staff Climate Champions Group | Underway | On time | • Staff Eco Group / Eco Champions [completed 31 Mar 2024] • Sustainability Themed Posts on the Staff Intranet [in progress, due date: 31 Mar 2024] |  |  | Planning & Regulation | 0 | No | 2025-06-26 15:03
TR1 | Decarbonising the Council's fleet and fuel | Underway | On time | • Incorporation of electric vans to the Council's fleet [in progress, due date: 31 Mar 2026] • Council's fleet electrification assessment [in progress, due date: 31 Mar 2026] • Switch to Hydrotreated Vegetable Oil (HVO) to run Council's fleet and machinery [completed 1 Oct 2024] • Installation of solar roofs on waste collection lorries [completed 23 Oct 2023] | Direct Services | Planning & Regulation |  | 0 | No | 2025-06-23 18:06
TR2 | Incentives for Council's staff sustainable commuting | Underway | On time | • Smart Go Stevenage membership [in progress, due date: 31 Mar 2026] • Cycle to Work Scheme implementation [in progress, due date: 31 Mar 2026] • Conduct a staff survey to assess commuting baseline [completed 5 Jan 2024] • Produce and implement a Workplace Travel Plan 2020-2025 [completed 31 Dec 2019] | Planning & Regulation |  |  | 0 | No | 2025-07-04 12:47
TR3 | Implement a borough-wide cycle hire scheme | Underway | On time | • Monitor the cycle hire scheme [in progress, due date: 31 Mar 2026] • Cycle-hire scheme re-launch [in progress, due date: 30 Jun 2025] • Cycle hire scheme launch [completed 1 Oct 2024] • Agree positioning of bays with HCC Highways and other stakeholders [completed 15 Aug 2024] • Agree scheme funding and phasing [completed 31 Mar 2024] • Tender for the scheme [completed 4 Dec 2023] | Planning & Regulation |  |  | 0 | No | 2025-07-04 10:57
TR4 | Planning policy for Electric Charging Infrastructure (all new developments) | Completed | On time |  | Planning & Regulation |  |  | 0 | No | 2025-06-23 14:43
TR5 | Deployment of public Electric Charging Infrastructure across Stevenage | Continuous Action | On time | • Installation of charging points across town using LEVI funding [in progress, due date: 1 Oct 2025] • Neighbourhood Centre EV charge point project [completed 31 May 2024] • Installation of Blink EV chargers at Swingate, The Forum and St Georges MSCP [completed 16 May 2023] • Installation of 30 EV charging points at the new Railway North MSCP (Stevenage Station) [completed 5 May 2023] • Bid for ORCS public EV charger funding from OZEV [completed 31 Mar 2023] | Planning & Regulation | Hertfordshire County Council; Regeneration |  | 1 | No | 2025-07-04 13:49
TR6 | Create and implement a low and zero emissions taxi strategy | Completed | On time | • Report to General Purposes Committee [completed 14 Dec 2023] • Second public consultation on the draft revised policy and conditions. [completed 14 Nov 2023] • Initial Taxi Policy Public Consultation [completed 28 Feb 2023] | Planning & Regulation |  |  | 0 | No | 2025-07-04 12:07
TR7 | Build new sustainable Bus Interchange | Completed | On time | • Construction complete [completed 26 Jun 2022] • Planting within the landscape [completed 26 Jun 2022] • Sustainable Features [completed 26 Jun 2022] • Construction begins [completed 5 Jul 2021] | Regeneration |  |  | 0 | No | 2025-06-23 14:44
TR8 | Deploy zero emissions local buses | Planning stage | Cancelled or postponed | • New bus station to accept electric buses [cancelled, due date: 23 Oct 2023] • Secured funding for fully electric buses [completed 31 Mar 2022] | Hertfordshire County Council | Stevenage Borough Council |  | 0 | No | 2025-06-23 14:44
TR9 | Stevenage as a Sustainable Travel Town | Underway |  |  | Regeneration | Hertfordshire County Council; Planning & Regulation |  | 0 | No | 2025-06-23 14:45
TR10 | Introduce an electric vehicle (EV) car club | Completed | On time | • Creation of space on the highway for EV Car Club vehicles [completed 17 Mar 2023] • Procurement of an EV Car Club service [completed 17 Mar 2023] • Launch the EV Car Club scheme in Stevenage [completed 17 Mar 2023] | Planning & Regulation |  |  | 0 | No | 2025-06-23 14:45
TR11 | Installation of parcel lockers in the town | Underway | On time | • Sign Contract with InPost [completed 31 Jan 2023] • Present Idea to Commercial and Investment Working Group [completed 31 Mar 2022] | Commercial | Finance and Estates |  | 0 | No | 2025-06-23 20:44
TR12 | Decarbonise SBC's business travel & grey fleet | Underway | On time | • Implementation of a Council's Staff Cycle Hire Scheme [completed 1 Nov 2024] • Conduct a staff survey to assess business travel baseline [completed 5 Jan 2024] • Implement an Electric Vehicle (EV) Car Club [completed 17 Mar 2023] • Setup of an SBC pool bike scheme [completed 31 Dec 2019] • Produce a Workplace Travel Plan 2020-2025 [completed 31 Dec 2019] |  |  |  | 0 | No | 2025-06-23 14:45
WR1 | Increase Recycling Rates | Underway | On time | • Increase recycling rates from 40% to 60% by 2035 [in progress, due date: 1 Jan 2035] • Separate weekly food waste collections [in progress, due date: 31 Mar 2026] • Flat Block Recycling Pilot Scheme - Phase 2 [in progress, due date: 31 Mar 2026] • Host a Recycling Road Show [completed 25 Oct 2023] • Flat Block Recycling Pilot Scheme - Phase 1 [completed 31 Jul 2023] | Direct Services |  |  | 1 | Yes | 2025-06-24 14:04
WR2 | Reduce and Manage Food Waste | Underway | On time | • Separate weekly food waste collections [in progress, due date: 31 Mar 2026] • Commercial Food Waste Collections [completed 31 Mar 2025] • Promote the Worth Saving Campaign [completed 26 Oct 2023] • Promote Love Food, Hate Waste Campaign [completed 3 Apr 2023] | Direct Services |  |  | 0 | No | 2025-06-24 14:04
WR3 | Promote the reusing, repairing and avoidance of waste | Underway | On time | • Herts Confident Continence Reusable Scheme [in progress, due date: 31 Dec 2025] • Reusable Menstrual Products Scheme [in progress, due date: 31 Dec 2025] • Implement a Recycle your Cycle Scheme [in progress, due date: 31 Dec 2025] • Herts Reusable Nappy Scheme [in progress, due date: 31 Dec 2025] • Community Repair Cafe [in progress, due date: 30 Nov 2025] | Direct Services |  |  | 0 | No | 2025-06-24 14:05