## Actions
Identifier | Action | Implementation phase | Status | Tasks | Primary responsible party | Collaborator | Other responsible parties | Indicators | Has goals | updated at
BI1 | Develop an Amenity Tree Management Policy | Completed | On time | • Develop a new Stevenage Tree & Woodland Strategy [completed 4 Jun 2025] • Develop an Amenity Tree Management Policy [completed 20 Jan 2021] | Direct Services |  |  | 0 | No | 2026-07-28 14:58
BI2 | Implement and update tree replacement policies and strategies in the Partial Local Plan Update | Planning stage | On time | • New tree replacement policies in the Local Plan [completed 31 Dec 2025] • Include tree replacement policy in the Amenity Tree Management Policy [completed 20 Jan 2021] | Planning & Regulation |  |  | 0 | No | 2026-08-13 11:03
BI3 | Plant 4,000 trees in Stevenage by 2030 | Underway | On time | • 80 Trees around Stevenage [in progress, due date: 31 Jan 2027] • Your Tree Our Future 2026 [in progress, due date: 31 Dec 2026] • Three additional micro woods [completed 31 Jan 2026] • Your Tree Our Future 2025 [completed 31 Dec 2025] • Create 3 new micro woods [completed 31 Jan 2025] • Orchard Creation [completed 31 Dec 2023] • Create a new community woodland in Fairlands Valley Park [completed 24 Feb 2023] | Direct Services |  |  | 1 | No | 2026-08-12 16:21
BI4 | Develop a Stevenage Biodiversity Action Plan (BAP) 2024-2028 | Completed | On time | • Present to E&E Select Committee: final revision of 2024-2028 BAP. [completed 5 Nov 2024] • 2024-2028 revision presented to Cabinet for final approval and ratification. [completed 9 Oct 2024] • Commission Herts & Middlesex Wildlife Trust to review the current BAP [completed 30 Apr 2023] | Direct Services |  |  | 0 | No | 2026-08-04 11:02
BI5 | Develop a Meadow Management Framework | Underway | On time | • Enhancing Meadow Grassland - Town Wide [not started, due date: 31 Mar 2027] • Agree additional grassland meadow sites [in progress, due date: 30 Sep 2025] • Deliver additional grassland management sites [completed 25 Mar 2022] | Direct Services |  |  | 0 | No | 2026-08-12 16:37
BI6 | Identify and measure Carbon Sinks | Planning stage | On time | • Identify potential large carbon storage habitats within Stevenage [in progress, due date: 31 Dec 2025] | Direct Services | Planning & Regulation |  | 0 | No | 2025-12-16 12:53
BI7 | Creation of Community Orchards | Continuous Action | On time | • Orchard management training provided to Green Space Volunteers to support ongoing management of the community orchards [in progress, due date: 31 Dec 2025] • New community orchard planted at Peartree Park, Letchmore Road Open Space and Bedwell Park [completed 15 Nov 2022] • New community orchards planted at Shephalbury Park, St Nicholas Park and Raleigh Crescent Open Space [completed 2 Dec 2021] • New community orchard in Hampson Park [completed 16 Mar 2021] • New community orchard in Wellfield Open Space [completed 16 Mar 2021] • New community orchard in Donkey Park [completed 16 Mar 2021] • New community orchard in Symonds Green [completed 31 Mar 2020] | Direct Services |  |  | 0 | No | 2025-12-16 12:55
BI8 | Implement and monitor Biodiversity Net Gain (BNG) | Underway | On time |  |  |  |  | 0 | No | 2026-08-12 16:44
BI9 | Develop a Green Spaces Strategy | Completed | On time | • Green Spaces Strategy approved by Cabinet [completed 4 Jun 2025] • Present to E&E Select Committee [completed 20 Mar 2025] • Public consultation to seek feedback on the draft Green Spaces Strategy [completed 23 Feb 2025] • Public engagement to inform site specific management plans for each of the principal parks [completed 15 Sep 2024] • Public consultation to inform the development of the strategy [completed 7 Jan 2024] |  |  |  | 0 | No | 2026-08-04 11:10
BI10 | Develop a Tree & Woodland Strategy | Completed | On time | • Strategy approved by Cabinet [completed 4 Jun 2025] • Present to E&E Select Committee [completed 20 Mar 2025] • Public consultation to seek feedback on the draft Tree & Woodland Strategy [completed 23 Feb 2025] • Public consultation to inform the development of the strategy [completed 5 Jan 2025] |  |  |  | 0 | No | 2026-08-04 11:11
BU1 | Supporting corporate sustainability for local businesses | Underway | On time | • Wenta's Action Zero Programme: Net-Zero Support for SMEs [in progress, due date: 31 Mar 2027] • Create a webpage on Sustainable Business Practice [completed 6 Feb 2024] • Sustainability Support through Community Renewal Funding [completed 31 Mar 2023] • Grow through Sustainability Conference 2022 [completed 15 Mar 2022] | Planning & Regulation |  |  | 0 | No | 2026-08-07 15:16
BU2 | Develop and implement a Sustainable Business Programme | Underway | On time | • Stevenage Green Business Grant [in progress, due date: 31 Dec 2026] • Small Business Sustainability Support Programme [completed 31 Mar 2026] • Second Meet the Buyer Event (MTB) [completed 25 Jun 2024] • Phase 2: 1-Day Intensive Workshop for Medium Sized Businesses [completed 20 Nov 2023] • First Meet the Buyer Event (MTB) [completed 28 Sep 2023] | Planning & Regulation |  |  | 0 | No | 2026-08-07 15:16
BU3 | Implement sustainable procurement for the Council | Underway | On time | • Include and monitor Social Value considerations in Council's procurement processes [in progress, due date: 31 Mar 2027] • Update and revise the Cooperative Procurement Strategy for 2025-2028 [completed 12 Mar 2025] • Participate in the RCCF Sustainable Procurement Sub Group [completed 31 Mar 2025] • Take part in the EELGA Responsible Procurement Diagnostic project [completed 31 Mar 2024] • Develop a Cooperative Procurement Strategy [completed 23 Nov 2021] | Finance and Estates |  |  | 0 | No | 2026-08-07 15:17
CR1 | Integrate sustainability & climate resilience within the SG1 Regeneration Programme | Completed | On time | • Include Climate Change Principles in the SG1 Development Proposal [completed 30 May 2023] • Submitted Planning Supporting Documents, including Energy Strategy, Sustainability Statement, Ecological Enhancement Strategy, Transport Assessment, Air Quality Assessment, Noise Impact Assessment, and Flood Risk Assessment. [completed 24 Dec 2019] | Planning & Regulation; Regeneration |  |  | 0 | No | 2026-08-07 15:36
CR2 | Update the Local Plan to incorporate new climate policies | Continuous Action | On time | • Upgrade the Local Plan with improved Climate Change policies [completed 22 Jul 2026] • Implement Stevenage Design Guide with Climate Change considerations [completed 1 Jan 2023] • To include climate change considerations in the Local Plan [completed 31 Dec 2020] | Planning & Regulation |  |  | 0 | No | 2026-08-07 15:37
CR3 | Zero carbon development for Station Gateway Area Action Plan (AAP) | Underway | On time | • Submission of the Local Plan to the Secretary of State [completed 22 Jul 2026] • Consult AAP/Local Plan Review through a Regulation 19 consultation [completed 14 Feb 2025] • Consult changes of AAP/Local Plan Review through a Regulation 18 consultation [completed 15 Aug 2025] • Incorporate AAP into Local Plan Review [completed 5 Jul 2025] • Public and Stakeholder consultation on the draft Preferred Options Report [completed 18 Jul 2023] • Responses to the public consultation on the Stevenage Connection Area Action Plan: Issues and Options Report. [completed 6 Sep 2021] • Public consultation on the Stevenage Connection Area Action Plan: Issues and Options Report. [completed 5 Sep 2021] • Publish the Sustainability Appraisal and Strategic Environmental Assessment screening [completed 22 May 2019] | Planning & Regulation |  |  | 0 | No | 2026-08-07 15:37
CR4 | Incorporate sustainability aspects into the new Railway North Multi Storey Car Park (MSCP) | Completed | On time | • Construction complete [completed 5 May 2023] • Construction begins [completed 23 May 2022] | Regeneration | Planning & Regulation |  | 0 | No | 2026-08-07 15:37
CR5 | Incorporate sustainability considerations into the new Leisure Centre | Underway | On time | • Planning permission granted [completed 9 Sep 2025] • Planning submission [completed 12 Jun 2025] • Refined Plans & Final Consultation [completed 9 Mar 2025] • Design Reveal & First Feedback [completed 31 Oct 2024] | Regeneration |  |  | 0 | No | 2026-08-07 15:39
EW1 | Free Water Refill in Town | Continuous Action |  |  | Planning & Regulation |  |  | 0 | No | 2026-07-16 13:37
EW2 | Rainwater Harvesting Pilot | Underway | On time | • Investigate additional opportunities for installing rainwater harvesting systems at Council's allotment sites [not started, due date: 1 Jul 2026] • Greydells Allotments Rainwater Harvesting [completed 1 May 2026] • Roebuck Community Rainwater Havesting [completed 31 Mar 2026] • Peartree Rainwater Collection Pilot [completed 31 Aug 2024] • Install 6 Water Butts at Garage Site on Whitesmead Road [completed 18 Oct 2023] | Direct Services | Planning & Regulation |  | 0 | No | 2026-07-16 15:28
EW3 | Reduce domestic water utilisation and improve efficiency | Underway | On time | • Tenant Sustainability Welcome Packs [not started, due date: 31 Dec 2026] • Enhance Water Efficiency related Policies within the Stevenage Local Plan [in progress, due date: 31 Dec 2025] | Planning & Regulation |  | Affinity Water | 0 | No | 2026-07-27 10:24
EW4 | Council estates energy efficiency and decarbonisation | Underway | On time | • Electricity monitoring through Grid Edge platform to identify efficiency opportunities [in progress, due date: 31 Mar 2027] • Town Centre Clocktower lighting system [completed 31 Dec 2025] • St George’s and Westgate Multi Storey Car Park (MSCP) upgrade programme [completed 31 Dec 2025] • Energy Efficiency Enhancement of Daneshill House [completed 31 Dec 2025] • Energy upgrades at SBC leisure facilities [completed 31 Dec 2025] • Conduct energy audits across SBC sites (electricity and gas) [completed 31 Jul 2023] • Boiler upgrade for SBC shelter housing [completed 31 Dec 2022] | Facilities | Finance and Estates; Planning & Regulation |  | 0 | No | 2026-08-06 10:15
EW5 | Zero carbon tariff for SBC electricity corporate contract | Completed | On time | • Switching to zero carbon electricity supply for SBC corporate contract [completed 4 Apr 2022] | Planning & Regulation |  |  | 0 | No | 2026-07-24 11:51
EW6 | Increase local renewable energy generation | Underway | On time | • Incorporate policies to support renewable energy generation in the Local Plan [completed 31 Dec 2025] • Round 3 - Solar Together Hertfordshire Scheme 2025 [completed 13 Jun 2025] • Complete a feasibility study on PV and battery storage installation for St George's Car Park alongside energy usage reduction [completed 1 May 2024] • Round 2 - Solar Together Hertfordshire 2023 [completed 31 Jul 2023] • Install Solar Panels on the New Railway North MSCP Development [completed 5 May 2023] | Planning & Regulation | Regeneration; Finance and Estates |  | 2 | No | 2026-08-12 16:05
HO1 | Decarbonisation of SBC Social Housing | Underway | On time | • Delivery of the Warm Homes: Social Housing Fund (Wave 3) [in progress, due date: 1 Jun 2028] • Decent Homes Upgrades [in progress, due date: 31 Mar 2027] • Major Refurbishment Programme [completed 28 Feb 2026] • Delivery of the Social Housing Decarbonisation Fund - Wave 2.1 [completed 17 Jun 2025] • Bid for Warm Homes: Social Housing Fund (Wave 3) [completed 25 Nov 2024] • Delivery of the Social Housing Decarbonisation Fund - Wave 1 [completed 31 Dec 2023] • Bid for Social Housing Decarbonisation Fund - Wave 2.1 [completed 31 Mar 2023] • Delivery of Local Authority Delivery Scheme 1B (LAD 1B) [completed 31 May 2022] | Housing & Investment |  |  | 1 | Yes | 2026-08-13 09:39
HO2 | Monitoring of Social Housing Energy Efficiency | Underway | On time | • Monitor the Council's housing stock using an Intelligent Energy System [in progress, due date: 31 Mar 2027] • Implement an Intelligent Energy System [completed 31 Dec 2022] | Housing & Investment |  |  | 0 | No | 2026-08-07 15:19
HO3 | Development of new sustainable Social Housing | Underway | On time | • Dunn Close [completed 31 Dec 2026] • Kenilworth Close (Phase 1) [completed 14 Jul 2024] • Helston House, Scarborough Avenue [completed 29 Dec 2023] | Housing Development |  |  | 0 | No | 2026-08-07 15:20
HO4 | Garages refurbishment and improvement programmes | Completed | On time | • SBC Garages Asset Management Plan (2025-2035) [in progress, due date: 31 Mar 2035] • Garages Refurbishment Programme [completed 31 Aug 2024] | Garages |  |  | 0 | No | 2026-08-18 09:41
HO5 | Decarbonisation of existing private domestic housing | Underway | On time | • Hertfordshire Local Retrofit Strategy 2025-28 [in progress, due date: 31 Dec 2028] • Delivery of Warm Homes: Local Grant (WHLG) [in progress, due date: 31 Mar 2028] • Energy Company Obligation Scheme - Round 4 (ECO 4) & GBIS [completed 31 Mar 2026] • Promotion of the Solar Together Scheme 2024-2025 [completed 25 Apr 2025] • Delivery of Home Upgrade Grant Phase 2 (HUG2) [completed 2 Dec 2024] • Submit EOI to Warm Homes: Local Grant [completed 1 Dec 2024] • Promotion of Hertfordshire Energy Advice Tool (HEAT) App [completed 31 Dec 2023] • Promotion of the Solar Together Scheme 2023 [completed 27 Oct 2023] • Delivery of Sustainable Warmth (LAD3 - HUG1) [completed 31 Mar 2023] • Delivery of Local Authority Delivery Scheme 2 (LAD2) [completed 30 Sep 2022] • Energy Company Obligation Scheme - Round 3 (ECO 3) [completed 31 Mar 2022] | Planning & Regulation |  |  | 1 | No | 2026-08-07 15:24
HO6 | Communal heating upgrade of Sheltered Housing | Completed | On time |  | Housing & Investment |  |  | 1 | No | 2026-08-07 15:24
PA1 | Implement Climate Emergency education for residents & visitors | Underway | On time | • Tenant Sustainability Welcome Packs [not started, due date: 31 Dec 2026] • Stevenage Day 2026 [completed 14 Jun 2026] • Stevenage Day 2025 [completed 8 Jun 2025] • Climate/Environmental Dates Calendar 2025 [completed 31 Dec 2024] • Stevenage Day 2024 [completed 6 Jul 2024] • Develop a Climate Change Communications Programme [completed 28 Jun 2024] • Stevenage Day 2023 [completed 10 Jun 2023] • Special storytime at Stevenage Central library [completed 15 Apr 2023] | Corporate Strategy & Transformation | Planning & Regulation |  | 0 | No | 2026-07-27 12:07
PA2 | Participate in the Council's Climate Action Scorecards assessment | Completed | On time | • Review Scorecards 2025 results [completed 31 Jul 2025] • Submit responses to Climate Action Scorecards 2025 [completed 31 Dec 2024] | Planning & Regulation |  |  | 0 | No | 2026-07-27 12:21
PA3 | Develop a Council's Climate Change Risk Assessment and Action Plan | Underway | On time | • Stevenage Borough Council Climate Adaptation Plan [in progress, due date: 31 Dec 2026] • Incorporate identified climate risks into the Operational Risks [in progress, due date: 1 Jul 2026] • Update the CCRA aligned with a DEFRA Adaptation Reporting Power (ARP) pilot project [completed 20 Jun 2025] • SBC First Climate Change Risk Assessment [completed 6 Aug 2024] • Service leads to review identified climate risks draft [completed 14 Jun 2024] • Climate Action team to draft climate risks [completed 10 Apr 2024] • Complete an Extreme Weather Survey [completed 30 Jun 2023] | Planning & Regulation |  |  | 0 | No | 2026-07-24 11:52
PA4 | Develop and implement a Climate Change Community Fund (CCCF) | Underway | On time | • Continuously assess, approve, fund and monitor CCCF projects [in progress, due date: 31 Mar 2027] • Revise the CCCF Requirements and Application Process [completed 7 Jun 2024] • Create and Publish the CCCF Webpage [completed 7 Jun 2024] • Design and Distribute a CCCF Flyer [completed 31 Jan 2024] • Test 2 Pilot Projects [completed 31 Mar 2024] | Planning & Regulation |  |  | 0 | No | 2026-07-28 11:02
PA5 | Promote event sustainability across the town | Underway | On time | • Discourage single-use plastic at refreshment and catering units at SBC events. [completed 6 Jul 2024] • Develop Sustainability Guidance as an integral part of the Community Event Toolkit [completed 24 May 2024] | Communities & Neighbourhoods |  |  | 0 | No | 2026-07-28 11:47
PA6 | Add "Tackling Climate Change" as priority of our Council's Corporate Plan | Completed | [5 empty] | 0 | No | 2026-08-04 10:29
PA7 | Recurrent Annual Greenhouse Gas Reporting | Underway | On time | • Collect Financial Year 2025/26 Emissions Data [in progress, due date: 1 Oct 2026] • Draft Emissions Reporting Framework [completed 1 May 2026] • Review 2018 Baseline Data [completed 1 Feb 2026] • Collect Financial Year 2023/24 Emissions Data [completed 1 Feb 2026] • Collect Financial Year 2024/25 Emissions Data [completed 1 Feb 2026] | Planning & Regulation |  |  | 0 | No | 2026-07-28 19:37
PA8 | Organise a Staff Climate Champions Group | Underway | On time | • Establish working subgroups [completed 31 Mar 2026] • Sustainable Buildings Certification Training [completed 31 Oct 2024] • Carbon Literacy Training for staff [completed 30 Sep 2024] • Establish Staff Eco Group / Eco Champions [completed 31 Mar 2024] • Sustainability Themed Posts on the Staff Intranet [completed 31 Dec 2024] |  |  | Planning & Regulation | 0 | No | 2026-07-28 12:11
TR1 | Decarbonising the Council's fleet and fuel | Underway | On time | • HVO Emissions Reductions Monitoring [in progress, due date: 31 Mar 2027] • Council's Fleet Electrification Assessment [in progress, due date: 31 Mar 2027] • Incorporation of electric vehicles to the Council's fleet [in progress, due date: 31 Mar 2027] • Switch to Hydrotreated Vegetable Oil (HVO) to run Council's fleet and machinery [completed 1 Oct 2024] • Installation of solar panels on waste collection lorries roofs [completed 23 Oct 2023] | Direct Services |  |  | 0 | No | 2026-08-07 15:26
TR2 | Incentives for Council's staff sustainable commuting | Underway | On time | • Smart Go Stevenage Membership [in progress, due date: 31 Mar 2027] • Cycle to Work Scheme Implementation [in progress, due date: 31 Mar 2027] • Setup a Sustainable Travel Climate Champions Working Group [in progress, due date: 31 Mar 2027] • Produce and Communicate a Sustainable Travel Induction Pack for Staff [completed 30 Nov 2025] • Conduct a Staff Travel Survey to assess commuting baseline [completed 5 Jan 2024] • Produce and implement a Workplace Travel Plan 2020-2025 [completed 31 Dec 2019] | Planning & Regulation |  |  | 0 | No | 2026-08-07 15:27
TR3 | Implement a borough-wide Cycle Hire Scheme | Underway | On time | • Monitor the Cycle Hire Scheme [in progress, due date: 31 Mar 2027] • Cycle Hire Scheme Re-Launch [completed 31 Dec 2025] • Stevenage's Cycle Hire Scheme Launch [completed 1 Oct 2024] • Agree positioning of bays with HCC Highways and other stakeholders [completed 15 Aug 2024] • Agree Scheme Funding and Phasing [completed 31 Mar 2024] • Tender for the Cycle Hire Scheme [completed 4 Dec 2023] | Planning & Regulation |  |  | 0 | No | 2026-08-07 15:27
TR4 | Planning Policy for EV Charging Infrastructure | Completed | On time |  | Planning & Regulation |  |  | 0 | No | 2026-08-07 15:27
TR5 | Deployment of public Electric Charging Infrastructure across Stevenage | Continuous Action | On time | • Installation of EV charging points across town using LEVI funding [in progress, due date: 31 Mar 2027] • Neighbourhood Centre EV Charge Point Project [completed 31 May 2024] • Installation of Blink EV Chargers at Swingate, The Forum and St Georges MSCP [completed 16 May 2023] • Installation of 30 EV Charging Points at Railway North MSCP [completed 5 May 2023] • Bid for ORCS Public EV Charger funding from OZEV [completed 31 Mar 2023] | Planning & Regulation | Hertfordshire County Council |  | 1 | No | 2026-08-07 15:28
TR6 | Create and implement a low and zero emissions taxi strategy | Completed | On time | • Implement reduced taxi licensing fees for Low and Zero Emission vehicles [completed 8 Oct 2025] • Hackney Carriage and Private Hire Policy implementation [completed 1 Apr 2024] • Report to General Purposes Committee and adoption [completed 14 Dec 2023] • Second public consultation on the draft revised policy and conditions. [completed 14 Nov 2023] • Initial Taxi Policy Public Consultation [completed 28 Feb 2023] | Planning & Regulation |  |  | 0 | No | 2026-08-07 15:29
TR7 | Build new sustainable Bus Interchange | Completed | On time | • Construction complete [completed 26 Jun 2022] • Planting within the landscape [completed 26 Jun 2022] • Sustainable Features [completed 26 Jun 2022] • Construction begins [completed 5 Jul 2021] | Regeneration |  |  | 0 | No | 2026-08-07 15:29
TR8 | Deploy zero emissions local buses | Planning stage | Cancelled or postponed | • New bus station to accept electric buses [cancelled, due date: 23 Oct 2023] • Secured funding for fully electric buses [completed 31 Mar 2022] | Hertfordshire County Council | Stevenage Borough Council |  | 0 | No | 2026-08-07 15:29
TR9 | Stevenage as a Sustainable Travel Town | Underway |  |  | Regeneration | Hertfordshire County Council; Planning & Regulation |  | 0 | No | 2026-08-07 15:30
TR10 | Introduce an electric vehicle (EV) car club | Completed | On time | • Creation of space on the highway for EV Car Club vehicles [completed 17 Mar 2023] • Procurement of an EV Car Club service [completed 17 Mar 2023] • Launch the EV Car Club scheme in Stevenage [completed 17 Mar 2023] | Planning & Regulation |  |  | 0 | No | 2026-08-07 15:30
TR11 | Installation of parcel lockers in the town | Underway | On time | • Contract signed with InPost [completed 31 Jan 2023] • Present Idea to Commercial and Investment Working Group [completed 31 Mar 2022] | Commercial | Finance and Estates |  | 0 | No | 2026-08-07 15:31
TR12 | Decarbonise SBC's business travel & grey fleet | Underway | On time | • Implementation of a Council's Staff Cycle Hire Scheme [in progress, due date: 31 Mar 2027] • Setup a Sustainable Travel Climate Champions working group [in progress, due date: 31 Mar 2027] • Produce and communicate a Sustainable Travel Induction Pack for staff [completed 30 Nov 2025] • Conduct a staff survey to assess business travel baseline [completed 5 Jan 2024] • Implement an Electric Vehicle (EV) Car Club [completed 17 Mar 2023] • Produce a Workplace Travel Plan 2020-2025 [completed 31 Dec 2019] • Setup of an SBC pool bike scheme [completed 31 Dec 2019] | Planning & Regulation |  |  | 0 | No | 2026-08-07 15:31
WR1 | Increase Recycling Rates | Underway | On time | • Increase recycling rates from 40% to 60% by 2035 [in progress, due date: 1 Jan 2035] • Kerbside Flexible Plastics Recycling [in progress, due date: 1 Apr 2030] • Flat Block Recycling Pilot Scheme - Phase 2 [completed 31 Dec 2025] • Neighbourhood Recycling Bring-Bank Sites [completed 31 Mar 2025] • Host a Recycling Road Show [completed 25 Oct 2023] • Flat Block Recycling Pilot Scheme - Phase 1 [completed 31 Jul 2023] | Direct Services |  |  | 1 | Yes | 2026-08-11 10:15
WR2 | Reduce and Manage Food Waste | Underway | On time | • Separate weekly food waste collections [completed 31 Mar 2026] • Commercial Food Waste Collections [completed 31 Mar 2025] • Promote the Worth Saving Campaign [completed 26 Oct 2023] • Promote Love Food, Hate Waste Campaign [completed 3 Apr 2023] | Direct Services |  |  | 0 | No | 2026-07-27 11:25
WR3 | Promote the reusing, repairing and avoidance of waste | Underway | On time | • Reusable Menstrual Products Scheme [in progress, due date: 31 Mar 2027] • Herts Confident Continence Reusable Scheme [in progress, due date: 31 Mar 2027] • Implement a Recycle your Cycle Scheme [in progress, due date: 31 Mar 2027] • Herts Reusable Nappy Scheme [in progress, due date: 31 Mar 2027] • Community Repair Cafe [completed 30 Nov 2025] | Direct Services |  |  | 0 | No | 2026-07-27 11:20
TR13 | Support cycling infrastructure across Stevenage | Underway | On time | • Lockable Bike Shelters Installation [in progress, due date: 31 Mar 2027] • Underpasses Improvements [in progress, due date: 31 Mar 2027] • Bikes Maintenance Stands Installation [completed 31 Dec 2025] |  |  |  | 0 | No | 2026-07-29 11:42